REQUEST FOR EXPRESSION OF INTEREST

SELECTION OF INDIVIDUAL CONSULTANTS

CONSULTANCY FOR THE DEVELOPMENT OF A STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN THE SOUTHERN AFRICAN DEVELOPMENT COMMUNITY (SADC)

REFERENCE NUMBER: SADC/3/5/2/27

FEBRUARY 2019

- The SADC Secretariat is inviting Individual Consultants to submit their CV and Financial Proposal for the following services:

“CONSULTANCY FOR THE DEVELOPMENT OF A STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN THE SOUTHERN AFRICAN DEVELOPMENT COMMUNITY (SADC  ’’

The Terms of Reference defining the minimum technical requirements for these services are attached as Annex 1 to this Request for Expression of Interest.

2. 	Only Individual Consultants are eligible for this assignment provided that they fulfil the following eligibility criteria:

a)	they are not bankrupt or being wound up, are having their affairs administered by the courts, have entered into arrangements with creditors, have suspended business activities, are being subject of proceedings concerning those matters, or are being in any similar situations arising from similar procedures provided for in the national legislation or regulations of the SADC member states;

b)	they have not been convicted of offences concerning their professional conduct by a judgment, which has the force of res judicata; (i.e. against which no appeal is possible);

c)	they have not been declared guilty of grave professional misconduct proven by any means which SADC Secretariat can justify;

d)	they have fulfilled obligations related to the payments of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those countries where the contract is to be performed;

e)	they have not been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the SADC Secretariat' financial interests; or

f)	they are not being currently subject to an administrative penalty.

3.	The maximum budget for this contract is US $ US$14,000.00 inclusive of professional fees and reimbursable expenses.  Proposals exceeding this budget will not be accepted.

4.	Your Expression of Interest must be presented as per Standard Expression of Interest Forms attached as Annex 2 to this REOI, in the English language and be accompanied by copies of all the indicated supporting documents. If the supporting documents are not in English, these shall be accompanied by a certified translation into English.

5.	Your proposal in a sealed envelope clearly marked “REFERENCE NUMBER: SADC/3/5/2/27“ CONSULTANCY FOR THE DEVELOPMENT OF A STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN THE SOUTHERN AFRICAN DEVELOPMENT COMMUNITY (SADC)

” should be submitted in our tender box located at the following address:

Secretary to the Tender Committee

SADC Secretariat

Plot 54385 CBD

Private Bag 0095

Gaborone

Botswana

6.	The deadline for submission of your proposal, to the address indicated in Paragraph 5 above, is 21st march 2019; 1600hours local time.

7.	Proposals submitted by E-mail are acceptable and should be submitted to fanr012019@sadc.int. by the deadline in Paragraph 6 above

8.	Your CV will be evaluated against the following criteria.

| Category | Points |
| --- | --- |
| Qualification in Education | 20 |
| Specific Skills | 70 |
| General Skills | 10 |
| Total | 100 |

9.	Your proposal should be submitted as per the following instructions and in accordance with the Terms and Conditions of the Standard Contract attached as Annex 3 to this REOI:

(i) 	PRICES:

The financial proposal shall be inclusive of all expenses deemed necessary by the Individual Consultant for the performance of the contract.

(ii)	EVALUATION AND AWARD OF THE CONTRACT:

Expressions of Interest determined to be formally compliant to the requirements will be further evaluated technically.

An Expression of Interest is considered compliant to the requirements if:

- It fulfils the formal requirements (see Paragraphs 2,3,4,5,6, 7, 8 and 9 above),

- The financial proposal (professional fees) does not exceed the maximum available budget for the contract as indicated under Para 3.

The award will be made to the applicant who obtained the highest technical score and with the financial offer (professional fees) within the budget as indicated under Para 3. Expressions of Interest not obtaining a minimum technical score of 70% will be rejected.

(iii) 	VALIDITY OF THE EXPRESSION OF INTEREST:

Your Expression of Interest should be valid for a period of 90 days from the date of deadline for submission indicated in Paragraph 6 above.

10. 	The assignment is expected to commence within two (2) weeks from the signature of the contract.

11.	Additional requests for information and clarifications can be made until 10 calendar days prior to deadline indicated in the paragraph 6 above, from:

The Procuring entity: SADC Secretariat

Contact person: Dr Gaolathe Thobokwe

Telephone: +267 3951863

Fax:+2673972848

E-mail:  gthobokwe@sadc.int  Copy to ggwaza@sadc.int

The answer on the questions received will be sent to the Consultant and all questions received as well as the answer(s) to them will be posted on the SADC Secretariat’s website at the latest 7 calendar days before the deadline for submission of the proposals.

ANNEXES:

ANNEX 1: Terms of Reference

ANNEX 2: Expression of Interest Forms

ANNEX 3: Standard Contract for Individual Consultants

Sincerely,

_____________________

Name: Gift Mike Gwaza

Title: Head of Procurement Unit

ANNEX 1: TERMS OF REFERENCE

SOUTHERN AFRICAN DEVELOPMENT COMMUNITY

TERMS OF REFERENCE

FOR

CONSULTANCY FOR THE DEVELOPMENT OF A STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN THE SOUTHERN AFRICAN DEVELOPMENT COMMUNITY (SADC)

11 SEPTEMBER 2018

| Action | Responsible Officer | Signature and Date |
| --- | --- | --- |
| Prepared by | Dr G Thobokwe PO - Livestock |  |
| Reviewed by | Ms P Elago Ag SPO – FS |  |
| Requested by | Mr D Gove Director FANR |  |
| Approved | Dr. Thembinkosi Mhlongo Deputy Executive Secretary (RI) |  |

- Introduction

The farm animal resources of Southern African Development Community (SADC) are rich and immensely diverse, with livestock populations in SADC estimated at 64 million cattle, 39 million sheep, 38 million goats, 7 million pigs, 1 million horses and 380 million poultry, ranking it amongst the most endowed regions of the continent in terms of livestock resources. Traditionally, these farm animals are a source of food, skins, fertilizer, traction power, medicine and other raw materials for the population of the region. An estimated 75% out of the above livestock population is kept under smallholder traditional farming systems. In addition, the region is endowed with a rich and diverse wildlife population.

Farm animal and wildlife genetic resources are valuable and strategically important assets for food, financial security and socio-cultural benefits of the peoples of Southern Africa. Domestic livestock production is crucial for sustainable agricultural production systems and for future food security and poverty alleviation in Africa. Farm animal genetic resources (FAnGRs) contribute significantly to the SADC economy and play a vital role in sustaining the livelihoods of many smallholder and agro-livestock systems in the region.  The demand for food of animal origin is increasing rapidly in developing countries more rapidly than the increase in production; therefore, a Livestock Revolution is needed (Delgado et al. 1999). Per capita consumption of livestock products was projected to increase for meat from 14 kg in 2005/07 to 26 kg in 2050; for milk 30 liters in 2005/2007 to 64 liter in 2050; while total consumption for meat was projected to increase from 11 million tons in 2005/07 to 35 million tons in 2050 (+218%) and for milk from 32 million tons in 2005/07 to 83 million tons in 2050(+159%).

The rising demand for food of animal origin and other livestock commodities has, to a large extent, been met by increasing the number of animals. This cannot continue because it often results in overstocking, land degradation and other negative impacts. The tendency therefore has been to improve productivity per animal and per unit area of land by introducing high yielding exotic breeds or their crosses. This has put the indigenous animal genetic resources at risk of the high yielding exotic breeds. Crossbreeding with exotic breeds without a long-term plan on how to maintain a suitable level of ‘upgrading’ and how to maintain the pure indigenous breeds for future will lead to extinction of the latter. Lack of or incomplete analysis of the different roles that livestock play in SADC specific ecosystem, usually leads to inappropriate and unsustainable breeding objectives, insufficient recording of livestock traits, and neglect of the potential and real value of various indigenous livestock breeds  Indigenous livestock breeds of various species have been adapted over many thousands of years to local environmental conditions and have demonstrated their superiority to survive and produce in harsh tropical environments. Some genotypes have proven to be more adapted to certain environments than others. This genetic variability provides the basis for any future conservation efforts.

The global situation on domestic animal diversity shows a gloomy picture: about 30% of the world’s livestock breeds are currently under threat of extinction; a large proportion of these are found in developing countries. There are no conservation programs for more than 75% of the threatened breeds. Biodiversity of farm animal genetic resources (FAnGR) has been rapidly declining in recent decades (FAO, 1999; Hammod and Leitch, 1996). These together with many of our wild animal species, if not preserved and protected, are seriously threatened.

Globalization, rapid population growth, urbanization, poaching and other human interferences, coupled with the ever increasing demand for foods and products of animal origin, have negatively exerted pressure on the animal genetic resources. This has led to a rapid decline of the biodiversity of animal resources and posed a challenge to the relevant international, regional and national bodies on how best to protect animal genetic resources. The loss of animal biodiversity concerns both wildlife and farm animal species. The rich SADC terrestrial and aquatic animal genetic resources must therefore be protected and sustained for present and future development of the region. It is therefore significant that the SADC puts in place and implements appropriate policies, laws and strategies to safeguard the region’s animal genetic resources.

SADC Member States have obligation to conserve their animal genetic resources (AnGRs) under the national,  regional and  international Agreements, Protocols, Policies, laws, Strategies, Plans and Programmes, to which most of them are signatory . These include: The Charter establishing SADC (1980); The SADC RISDP; The SADC Regional Agriculture Policy (RAP); The SADC Livestock Development Program; The world Conservation Strategy (1980); The Convention on Biological Diversity; The Global Plan of Action for Animal Genetic Resources and the Interlaken Declaration (2007);  The Convention on Biological Diversity Strategic Plan for Diversity 2011-2020, and  Many national policies, laws strategies and programmes.

  - Conservation

A conservative global estimate suggests that at least 28% of farm animal breeds became extinct, rare or endangered in the past century (World Conservation Monitoring Centre, 1992). In most marginal areas, AnGR-based farm systems are among the most important land-uses. Areas currently considered “marginal” have long been the source of several well-adapted local breeds, many of which are presently endangered, either because of substitution with (mostly exogenous) ‘improved’ breeds or because farmers abandon husbandry and agriculture. It is a widely held belief that the existence of such traditional, well-adapted breeds is a necessary given for viable, sustainable land use in marginal areas (Rege and Gibson, 2003). Indicators on the status of endangerment of breeds are available from many sources, but currently,  the most widely reported indicators pertinent to livestock biodiversity are found in the list provided by FAO through the “Domestic Animals Diversity – Information System (DAD-IS) and the Animal Genetic Data Bank of the European Association for Animal Production (EAAP). The EAAP data bank monitors information on populations at breed and country levels to keep an eye on development, on the change in the risk of breed extinction and to encourage use and conservation of animal genetic diversity. The farm animal species concerned are buffalo, cattle, goat, sheep, horse, ass, pig, and rabbits. In total, the data bank concerns 46 EAAP member countries and other European countries. Over the past decade, the FAO has helped collecting data from some 170 countries on almost 6,500 breeds of domesticated mammals and birds: cattle, goats, sheep, buffalo, yaks, pigs, horses, rabbits, chickens, turkeys, ducks, geese, pigeons, even ostriches. The FAO Global Databank for Farm Animal Genetic Resources (DAD-IS) contains information on 6,379 breeds of 30 mammalian and bird species. Population size data is available for 4,183 breeds of which 740 breeds are already extinct and 1,335, or 32%, are classified at high risk of loss and are threatened by extinction (Philipsson et al., 2011).

The United Nations Convention on Biological Diversity (CBD) of 1992 emphasized the need to conserve the world’s biological diversity, including FAnGR, for present and future use. In 2001 FAO launched a global program to monitor animal genetic resources, analyze their status and support the development of national or regional action plans, including conservation schemes. The SADC RISDP emphasize the need to put in place mechanisms for the preservation of AnGRs. To successfully undertake these schemes, in-depth knowledge of the status quo, gaps, key players in the area of conservation of animal genetic resources is essential.

- Regional Strategy initiative

The purpose of this consultancy is to develop a regional strategy that will guide the conservation and utilization of animal (livestock, wildlife and aquatic) genetic resources in the SADC region. The strategy will identity key priority areas and strategic intervention areas for conservation and utilization of relevance to the SADC regions’ animal resources and environment. The Strategy will also suggest management structures for conservation and utilization of SADC regions’ animal resources

- Overall Objective

To formulate a comprehensive Regional Strategy for the Conservation and utilization of Animal Genetic Resources in the Southern African Development Community (SADC)

3.1 Specific Objectives:

- To harmonise  the regional Animal Genetic resources conservation and utilization strategies

- To harmonize coordination Mechanisms for national and regional AnGRs effort;

- To address Policy and Legal development  issues;

- To address key factors causing threats to AnGRs and the dynamics of the threats and how to mitigate them;

- To strengthen the National Animal Genetic Conservation Programs through capacity-building, upgrading  and management requirements;

- Address infrastructures development, upgrading facilities and identifying Center for animal genetic resource conservation or Center for Excellence for the region;

- To initiate implementation of Joint Research Projects And  Cross border ventures;

- Indicate Collaboration mechanisms  with Regional/ International Organizations;

- To set up information and Knowledge Management (establishment of a Platform for information Sharing) and

- To establish an Implementation Framework for the strategy.

- To develop monitoring and evaluation framework of the strategy

- Scope of work

- Collection, collation and reviewing of SADC and Member States Policies and Strategies on animal genetic resources conservation and utilization.

- Review the international instruments on animal genetic  resources conservation and utilization that the SADC Partner States is committed to

- Identify institutional barriers as well as policy opportunities and promising institutions that are required to create environment that supports animal genetic resources conservation and utilization

- Identify key priority strategic areas and propose subsequent strategic areas to address the regional concerns in animal genetic conservation and utilization.

- Identify key actors in the SADC regional livestock sector and their roles in the animal genetic resources conservation and utilization

- Develop a monitoring and evaluation framework

- Prepare a draft background report and  SADC Animal Resources Conservation and utilization  on Strategy taking into consideration provisions of the The  SADC RISDP; The SADC Regional Agriculture Policy (RAP); The SADC Livestock Development Program

- Attend and participate as facilitator in all the regional draft strategy review and validation meetings

- Expected Results

The SADC Animal Genetic Resources Strategy will be the main output of the consultancy and will be an important landmark in efforts to have a coordinated effort to safeguard the region’s Animal Genetic Resources.

- Consultancy issues

- Identification of key barriers, priority areas and strategic issues for animal genetic resources conservation and utilization.

- Determine the drivers  and management structures of animal genetic resources conservation and utilization in the context of t production systems

- Assess the influence of climate change and variability on animal genetic resources conservation and utilization

- Duration of Consultancy

The work is programmed to take 40 days spread over 2 months. The consultancy start from March 2019 and should end by May 2019

- Deliverables

The initiate will generate a report, regional Strategy for the conservation of Animal Genetic Resources from which other regional animal genetic conservation efforts can benefit.

- Inception Report;

- Draft SADC Conservation and utilization  Animal Genetic Resources strategy;

- Background Report on status of Animal Genetic Resources conservation and utilization in the SADC.

- Methodology

The process of developing the strategy will be guided by the SADC consultative process of developing policy and legal instruments. In brief, this will involve national and regional bench reviews and consultations, interviews and validation workshop. The strategy will have a vision and a mission to guide the regional and national strategic aspirations for the Animal Genetics Resources (AnGRs).

In summary the consultant is expected to use a variety of approaches including but not limited to;

- Desk Top Studies

- In depth interviews  with stakeholders  from public and private sectors in 4 selected representative SADC Member States

- Collection, collation and analysis of national policies, strategies, laws and regulation amongst other policy instruments in the SADC region

- Facilitate validation meeting(s) to present the regional report and Draft Strategy on animal genetic resources conservation and utilization.

- Qualifications and Experiences required

- Must have a first degree in animal production/ sciences or veterinary medicine with a masters in animal breeding or livestock production systems/ animal production

- Must have 10 years’ experience in the livestock sector and especially in the area of animal genetic resources conservation and utilization/ animal production

- Must have 10 years’ experience in development of policies and strategies  especially in the livestock sector within SADC

- Must have good knowledge of SADC Member States animal resources sector

- Must be computer literate and capable of working independently

- Should be conversant with English

- Experience in strategic planning and policy analysis will be added advantage

- A PhD in the animal sciences, agricultural economics or any other relevant field will be added advantage

- Amount and Mode of Payment

The Consultant will be paid based on production of the stated deliverables. The consultancy fees will be 14,000 USD for the development of the strategy for a total of 40 man days and the assignment is spread over a period of 3 months.

Approved travels expenses will be paid separately. This will include air tickets and daily subsistence allowance (DSA) for approved field missions. These expenses will also be met by the SADC Secretariat. The missions will be approved by SADC Secretariat.

- Insurance cover

The consultants will be responsible for his/her own medical and life insurance cover for the duration of the assignment.

- Reporting

The consultant will report to the SADC FANR Directorate on day to day basis.

ANNEX 2: Expression of Interest Forms

A.	COVER LETTER FOR THE EXPESSION OF INTEREST FOR THE PROJECT	12

B.	CURRICULUM VITAE	14

C.	FINANCIAL PROPOSAL	18

# A.	COVER LETTER FOR THE EXPRESSION OF INTEREST FOR THE PROJECT

REFERENCE NUMBER: SADC/3/5/2/27

CONSULTANCY FOR THE DEVELOPMENT OF A STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN THE SOUTHERN AFRICAN DEVELOPMENT COMMUNITY (SADC)

Gaborone, 28th February 2019

To:	SADC Secretariat

Dear Sirs:

I, the undersigned, offer to provide the consulting services for the “DEVELOPMENT OF A STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN SADC’ ‘in accordance with your Request for Expression of Interests number SADC SADC/3/5/2/27-, dated [20th February 2019] for the sum of [Insert amount(s) in words and figures1].  This amount is inclusive of all expenses deemed necessary for the performance of the contract in accordance with the Terms of Reference requirements, and [“does” or “does not” delete as applicable] include any of the following taxes in Procuring Entity’s country: value added tax and social charges or/and income taxes on fees and benefits.

I hereby declare that all the information and statements made in my CV are true and accept that any misinterpretation contained in it may lead to my disqualification.

I take note that under the provisions of the SADC Procurement Policy applicable to this Request For Expression of Interest, a contract cannot be awarded to applicants who are in any of the following situations:

a)	they are being bankrupt or wound up, are having their affairs administered by the courts, have entered into arrangements with creditors, have suspended business activities, are being subject of proceedings concerning those matters, or are being in any similar situations arising from a similar procedures provided for in the national legislation or regulations of the SADC member states;

b)	they have been convicted of offences concerning their professional conduct by a judgment which haves the force of res judicata; (i.e. against which no appeal is possible);

c)	they have been declared guilty of grave professional misconduct proven by any means which SADC Secretariat can justify;

d)	they have not fulfilled obligations related to the payments of social security contributions or the payment of taxes in accordance with the legal provisions of the country in which they are established or with those countries where the contract is to be performed;

e)	they have been the subject of a judgment which has the force of res judicata for fraud, corruption, involvement in a criminal organisation or any other illegal activity detrimental to the SADC Secretariat' financial interests; or

f)	they are being currently subject to an administrative penalty.

I confirm that I am not in any of the situations described above, and I hereby declare that at any point in time, at the SADC Secretariat’s request, I will provide certified copies of documents to prove so.

I am aware that the penalties set out in the Procurement Policy may be applied in the case of a false declaration, should the contract be awarded to me.

My proposal is binding upon me for the period indicated in Paragraph 9(iii) of this Request for Expression of Interest.

I undertake, if my Proposal is accepted, to initiate the consulting services related to the assignment not later than the date indicated in Paragraph 10 of the Request for Expression of Interest, and to be available for the entire duration of the contract as specified in the Terms of Reference.

I understand you are not bound to accept any Proposal you receive.

Yours sincerely,

Signature [In full and initials]:

Name and Title of Signatory:

# B.	CURRICULUM VITAE

[insert full name]

| - Family name: | [insert the name] |
| --- | --- |
| - First names: | [insert the names in full] |
| - Date of birth: | [insert the date] |
| - Nationality: | [insert the country or countries of citizenship] |
| - Physical address: - Postal address - Phone: - E-mail: | [insert the physical address] [Insert Postal Address] [insert the phone and mobile no.] [Insert E-mail address(es) |
| - Education: |  |
| Institution: [Date from – Date to] | Degree(s) or Diploma(s) obtained: |
| [indicate the month and the year] | [insert the name of the diploma and the specialty/major] |
| [indicate the month and the year] | [insert the name of the diploma and the specialty/major] |

10.	Language skills: (Indicate competence on a scale of 1 to 5) (1 – excellent; 5 – basic)

| Language | Reading | Speaking | Writing |
| --- | --- | --- | --- |
| [insert the language] | [insert the no.] | [insert the no.] | [insert the no.] |
| [insert the no.] | [insert the no.] | [insert the no.] | [insert the no.] |

| 11. Membership of professional bodies: | [indicate the name of the professional body] |
| --- | --- |
| 12. Other skills: | [insert the skills] |
| 13. Present position: | [insert the name] |
| 14. Years of experience: | [insert the no] |
| 15. Key qualifications: (Relevant to the assignment) [insert the key qualifications] |  |

16.	Specific experience in the region:

| Country | Date from - Date to |
| --- | --- |
| [insert the country] | [indicate the month and the year] |
| ................ | ...................... |
| [insert the country] | [indicate the month and the year] |

17. Professional experience:

| Date from – Date to | Location of the assignment | Company& reference person (name & contact details) | Position | Description |
| --- | --- | --- | --- | --- |
| [indicate the month and the year] | [indicate the country and the city] | Name of the Company: Address of the company: Phone: Fax: Email: Name and title of the reference person from the company: | [indicate the exact name and title and if it was a short term or a long term position] | Name of the Assignment: Beneficiary of the Assignment: Brief description of the Assignment: Responsibilities: |
| [indicate the month and the year] | [indicate the country and the city] | Name of the Company: Address of the company: Phone: Fax: Email: Name and title of the reference person from the company: | [indicate the exact name and title and if it was a short term or a long term position] | Name of the Assignment: Beneficiary of the Assignment: Brief description of the Assignment: Responsibilities: |
| [indicate the month and the year] | [indicate the country and the city] | Name of the Company: Address of the company: Phone: Fax: Email: Name and title of the reference person from the company: | [indicate the exact name and title and if it was a short term or a long term position] | Name of the Assignment: Beneficiary of the Assignment: Brief description of the Assignment: Responsibilities: |
| ................ | …………….. | ……………………. | …………… | ………………………………………………………………………….. |
| [indicate the month and the year] | [indicate the country and the city] | Name of the Company: Address of the company: Phone: Fax: Email: Name and title of the reference person from the company: | [indicate the exact name and title and if it was a short term or a long term position] | Name of the Assignment: Beneficiary of the Assignment: Brief description of the Assignment: Responsibilities: |

- Other relevant information: (e.g. Publications)

[insert the details]

19. Statement:

I, the undersigned, certify that to the best of my knowledge and belief, this CV correctly describes myself, my qualifications, and my experience. I understand that any wilful misstatement described herein may lead to my disqualification or dismissal, if engaged.

I hereby declare that at any point in time, at the SADC Secretariat’s request, I will provide certified copies of all documents to prove that I have the qualifications and the professional experience as indicated in points 8 and 14 above, documents which are attached to this CV as photocopies.

By signing this statement, I also authorize the SADC Secretariat to contact my previous or current employers indicated at point 14 above, to obtain directly reference about my professional conduct and achievements.

|  | Date: |  |
| --- | --- | --- |

ATTACHMENTS: 	1) Proof of qualifications indicated at point 9
			2) Proof of working experience indicated at point 15

# C.	FINANCIAL PROPOSAL

REQUEST FOR SERVICES TITLE: DEVELOPMENT OF STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN SADC

REFERENCE NUMBER: SADC/3/5/2/27

| N° | Description |  | Unit | No. of Units | Unit Cost (in US$) | Total (in US$) |
| --- | --- | --- | --- | --- | --- | --- |
| Fees |  |  | Day |  |  |  |
| Reimbursable expenses, out of which |  |  | Total |  |  |  |
| 1 | Per diem allowances |  | Day | N/A |  |  |
| 2 | Flights |  | Trip | N/A |  |  |
| 3 | Miscellaneous travel expenses |  | Trip |  |  |  |
| 4 | Insurances cost, out of which: |  | Lump sum |  |  |  |
|  | i) | Life insurance (including repatriation) | Lump sum | N/A |  |  |
|  | ii) | Heath insurance | Lump sum | N/A |  |  |
|  | iii) | Third party liability insurance | Lump sum |  |  |  |
|  | iv) | Professional liability insurance | Lump sum | N/A |  |  |
| 5 | Drafting, reproduction of reports |  | Lump sum |  |  |  |
| 6 | Office rent |  | Per month | N/A |  |  |
| 7 | Others4 |  | TBD |  |  |  |
| TOTAL FINANCIAL OFFER (Fees + Reimbursable expenses) |  |  |  |  |  |  |

Signature [In full and initials]:

Name and Title of Signatory:

ANNEX 3: STANDARD CONTRACT FOR INDIVIDUAL CONSULTANTS

# STANDARD TERMS OF CONTRACT

# (Individual Consultant)

REFERENCE NUMBER SADC/3/5/2/27:  - DEVELOPMENT OF STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN SADC

THIS Contract (“Contract”) is made on [day] day of the month of [month], [year], between, on the one hand,

The SADC Secretariat (hereinafter called the “Procuring Entity”) with the registered business in:  Plot 54385 CBD, Private Bag 0095, Gaborone, Botswana

and, on the other hand,

[Insert the full name of the individual] (Hereinafter called the “Individual Consultant”), with residence in [insert the Individual Consultant’ address, phone, fax, email], citizen of [insert the Individual Consultant’s citizenship] owner of the ID/Passport Number [insert the number] issued on [insert the date] by [insert the name of the issuance authority],

WHEREAS, the Procuring Entity wishes to have the Individual Consultant perform the services hereinafter referred to, and WHEREAS, the Individual Consultant is willing to perform these services,

NOW THEREFORE THE PARTIES hereby agree as follows:

- Definitions

For the purpose of this contract the following definitions shall be used:

  - Procuring Entity means the legally entity, namely the SADC Secretariat who purchase the Services described in Annex 1 to this contract.

  - Contract means the agreement covered by these Terms including the Annexes and documents incorporated and/or referred to therein, and attachments thereto.

Contract value means the total price of the Financial Proposal included in the Individual Consultant’s Expression of Interests dated [insert the date] for the project SADC/3/5/2/27  - REQUEST FOR SERVICES TITLE: “DEVELOPMENT OF STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN SADC

’’

and reflected as such in the Annex 2 of this contract.

Individual Consultant means the individual to whom the Procuring Entity has awarded this contract following the Request for Expression of Interest SADC/3/5/2/27  - REQUEST FOR SERVICES TITLE: “DEVELOPMENT OF STRATEGY FOR CONSERVATION AND UTILIZATION OF ANIMAL GENETIC RESOURCES IN SADC

’’

  - Services means the Services to be performed by the Individual Consultant as more particularly described in Annex 1; for the avoidance of doubt, the Services to be performed include all obligations referred to in this Contract (as defined above).

- The Services

The Individual Consultant will undertake the performance of the Services in accordance with the provisions of the Annex 1 of this Contract and shall, in the performance of the Services, exercise all the reasonable skill, care and diligence to be expected of an Individual Consultant carrying out such services.

- Payment

  - The Individual Consultant shall be paid for the Services at the rates and upon the terms set out in Annex 2.

  - Payment shall be made to the Individual Consultant in US $ unless otherwise provided by this contract and where applicable, VAT shall be payable on such sums at the applicable rate. The Individual Consultant must, in all cases, provide their VAT registration number on all invoices.

  - Unless otherwise provided in this Contract, invoices shall be delivered to and made out to Procuring Entity and shall be paid within 30 days of receipt by the Project Director, subject to the Individual Consultant having complied with his/her obligations hereunder in full as stated in the Annex II to this Contract. The Procuring Entity reserves the right to delay and/or withhold, fully or partially, payments that have not been supported by full and appropriate supporting evidence that the services provided were delivered and accepted by the Procuring Entity.

- Status of the Individual Consultant

  - For the duration of the Contract, the Individual Consultant will have a status similar to the Procuring Entity’s contractor with regards to their legal obligations, privileges and indemnities in the Procuring Entity’s country.

  - The Procuring Entity will be responsible for ensuring all visas, work permits and other legal requirements to enable The Individual Consultant to live and work in the countries of the assignment as per the duties under the contract.

  - The Individual Consultant shall be responsible for paying any tax and social security contributions in his/her country of residence, for any activity deriving from this contract. Such costs shall be assumed included in the Individual Consultant’s fees.

  - The Procuring Entity shall be responsible for paying any taxes resulting from the activities performed under this contract imposed to the Individual in the country (ies) of the assignment with the exception of the ones set out in paragraph 4.3 above.

- Supervision of the Services

The Individual Consultant undertakes to deliver the Services in compliance with a system of quality assurance acceptable to the Procuring Entity which shall include any steps to comply with the standards operated by the Procuring Entity. The Individual Consultant shall be informed of the specific requirements in relation to this, and at the request of the Procuring Entity (s)he shall allow access to information, records and other materials during normal office working hours as the Procuring Entity may require in order to confirm that the work in progress is in accordance with these quality procedures.

- Compliance with this contract

The Procuring Entity will be entitled to seek confirmation from the Individual Consultant, at any time during the delivery of this contract, and for a period of 1 year after its completion, that the Individual Consultant has complied with the terms of this contract. It may also request the provision of reasonable documentary evidence to support this.  As stated in article 2.3 of this Contract, the Procuring Entity may delay or withhold payments in the event of non-compliance.

- Assignment and Subcontracting

  - The Individual Consultant shall under no circumstances sub-contract, sublet, assign or transfer the Contract or any part share or interest in it.  Where the Individual Consultant considers it necessary to use the services of a third party, (s)he shall inform the Procuring Entity’s Project Director in writing, and only once written approval is provided can the Consultant proceed to use a third party.

  - When the Project Director agrees that the activities under the contract can be performed by a third party, the third party involved in the delivery of services in this contract, will be under the direct control of the Individual Consultant. The Procuring Entity will not be responsible for the third party’s performance of duties or Services assigned to it, and neither for ensuring that conditions of employment are met nor for any other employment obligations relating to that person including, but not restricted to, taxation and insurance including professional indemnity insurance, employer’s liability insurance and public liability insurance.

- Breach of the Terms

In the event of a breach of any Terms of the Contract, the party not in breach may serve a notice on the party in breach requiring the breach to be remedied within a period specified in the notice, not normally being longer than 30 days.  If the breach has not been remedied before the expiry of the specified period, the party not in breach may then terminate the Contract in writing and may take appropriate steps to remedy the breach.

- Liability of the Individual Consultant

  - The Procuring Entity will be relying on the Individual Consultant’s skills, expertise and experience in relation to the performance of the Services in accordance with this contract and also upon the accuracy of all representations and statements made and the advice given in connection with the provision of the Services.

  - In view of the reliance by the Procuring Entity set out in 9.1 above, the Individual Consultant agrees to indemnify at its own expense, protect and defend the Procuring Entity, its agents and employees, from and against all actions, claims, losses or damages arising out of the Individual Consultant's performance of this contract provided that:

- the Individual Consultant is notified of such actions, claims, losses or damages not later than 30 days after the Procuring Entity becomes aware of them;

- the ceiling on the Individual Consultant's liability to the Procuring Entity shall be limited to an amount equal to the contract value but such ceiling shall not apply to any losses or damages caused to third parties by the Individual Consultant's willful misconduct; and

- the Individual Consultant's liability shall be limited to actions, claims, losses or damages directly caused by such failure to perform its obligations under the contract and shall not include liability arising from unforeseeable occurrences incidental or indirectly consequential to such failure.

  - At its own expense, the Individual Consultant shall, upon request of the Procuring Entity, remedy any defect in the performance of the services in the event of the Individual Consultant's failure to perform its obligations under the contract.

  - The Individual Consultant shall have no liability whatsoever for actions, claims, losses or damages occasioned by the Procuring Entity omitting to act on any recommendation, or overriding any act or decision of the Individual Consultant, or requiring the Individual Consultant to implement a decision or recommendation with which the Individual Consultant disagrees or on which (s)he expresses a serious reservation.

- Insurance

  - The Individual Consultant must ensure that full and appropriate professional indemnity insurance and third party liability insurance, is in place for all Services provided.

  - The cost of such insurances will be covered from reimbursable expenses of the contract.

  - Where national requirements or practices provide for different regulations/practices concerning insurance, the Individual Consultant may provide written confirmation of all insurances held and a signed declaration that these are in line with regulations/practices in their country of operation.  Only if such confirmation has been provided, and written confirmation of its acceptance provided to the Individual Consultant by the Procuring Entity, will this remove the obligation to meet the requirements of clause 11.1 of this Contract in full.

  - All insurances effected by the Individual Consultant shall be effected with an insurer of good repute and the Individual Consultant agrees to maintain such insurances for a period of 1 year from the completion of the Services under this Contract so long as such insurance continues to be available upon reasonable terms at reasonable commercial rates failing which Procuring Entity shall be entitled to take out insurance itself to cover any potential liability to its own Procuring Entity in relation to the performance of the Services under this contract. The cost of such insurance shall be a debt immediately due from the Individual Consultant.

  - The provisions of this clause shall remain in full force and effect notwithstanding the completion of the performance of the Services hereunder and the satisfaction of all other provisions of this contract.

- Copyright

  - Unless otherwise specified in the Contract, the title of the copyright and any other intellectual property rights arising out of the performance of this Contract shall be vested in the Procuring Entity which shall have the unfettered right to assign and grant sub-licenses in respect of the same. Except as permitted by the Terms of this Contract, the said materials shall not be reproduced or disseminated without proper consultation with, and written permission from, the Procuring Entity. This provision shall apply to the title to rights arising from the performance under this contract but shall not apply to the internal systems or rights in relation to the Individual Consultant’s own systems not created specifically for this purpose and where the same are an important part of the Services. The Individual Consultant shall grant a free and irrevocable license to the Procuring Entity and its assigns for the use of the same in that connection.

The Individual Consultant warrants that it is free of any duties or obligations to third parties which may conflict with this contract and, without prejudice to the generality of Term 9 above, agrees to indemnify the Procuring Entity against any and all actions, costs damages, direct, indirect or consequential, and other expenses of any nature whatsoever which the Procuring Entity may incur or suffer as a result of the breach by the Individual Consultant of this warranty.

- Non Disclosure & Confidentiality

  - The Individual Consultant will treat all information and results obtained in discharging the Services under this Contract as confidential and will not disclose by any means whatsoever such results or material to any third party without the prior written consent of the Procuring Entity and will only use such information for the purposes of this Contract. In addition, the Individual Consultant shall not make any communication to the press or any broadcast (including, but not limited to, inclusion of information on a website) about the Services without the prior written agreement of the Project Director.

  - If the Individual Consultant violates clause 12.1, then (s) he will automatically and legally be held to pay the amount estimated as the minimum reasonable damages resulting from a breach of confidentiality. This is without prejudice to the right of the Procuring Entity to demonstrate that a higher amount of loss has or may be incurred as a result of liabilities held by the Consultant in relation to the Procuring Entity.

- Suspension or Termination

  - In response to any factors out of the control of Procuring Entity and/or to breaches of contract by the Consultant, the Procuring Entity may at any time, by giving 30 days’ notice in writing, terminate in whole or in part or suspend the Individual Consultant’s performance of the Services. In such event, the Individual Consultant shall be entitled to payment pursuant to sub-clause 13.4 below.  If such suspension continues for a period in excess of twelve months, then either party may terminate this contract forthwith by written notice to the other.

  - The Individual Consultant may also terminate the contract unilaterally, without providing any reasons for such decision, if (s)he gives a 30 days prior written notice to the Project Director.

  - In the event of early termination of the Contract under sub-clauses 13.1, 13.2 and 13.3 of this clause, the Individual Consultant shall be entitled to a fair and reasonable proportion of the fees payable for that part of the Services carried out up to the date of such termination or suspension but this shall not include any loss of profit or contracts or any other expenses, losses or claims arising out of such termination or suspension or consequential thereupon.

- No Waiver

No forbearance shown or granted to the Individual Consultant, unless in writing by an authorized officer of the Procuring Entity, shall in any way affect or prejudice the rights of the Procuring Entity or be taken as a waiver of any of these Terms.

- Variations

Any variation to these terms or the provisions of the Annexes shall be subject to a written Addendum and be signed by duly authorized signatories on behalf of the Individual Consultant and the Procuring Entity respectively.

- Jurisdiction

This contract shall be governed by, and shall be construed in accordance with Botswana law and each party agrees to submit to the exclusive jurisdiction of the Botswana courts in regard to any claim or matter arising under this contract.

The following Annexes are integral part of this Contract:

Annex 1: Terms of Reference

Annex 2: Payment Schedule and Requirements

Signed today [insert the date] in four (4) originals in the English language by:

| For the Procuring Entity |  | For the Individual Consultant |  |
| --- | --- | --- | --- |
| Name : |  | Name : |  |
| Position : |  |  |  |
| Place : |  | Place : |  |
| Date: |  | Date : |  |
| Signature: |  | Signature: |  |

Annex 1: Terms of Reference

[insert the Terms of Reference]

Annex 2: Payment Schedule and Requirements

  - For Services rendered pursuant to Annex 1, the Procuring Entity shall pay the Individual Consultant an amount not to exceed the ceiling of US Dollars [insert ceiling amount], which shall be considered the contract value. This amount has been established based on the understanding that it includes all of the Consultant’s costs and profits as well as any tax obligation that may be imposed on the Individual Consultant in his/her country of residence.

  - The breakdown of prices is:

| N° | Description |  | Unit | No. of Units | Unit Cost (in US$) | Total (in US$) |
| --- | --- | --- | --- | --- | --- | --- |
| Fees |  |  | Day |  |  |  |
| Reimbursable expenses, out of which |  |  | Total |  |  |  |
| 1 | Per diem allowances |  | Day |  |  |  |
| 2 | Flights |  | Trip |  |  |  |
| 3 | Miscellaneous travel expenses |  | Trip |  |  |  |
| 4 | Insurances cost, out of which: |  | Lump sum |  |  |  |
|  | i) | Life insurance (including repatriation) | Lump sum |  |  |  |
|  | ii) | Heath insurance | Lump sum |  |  |  |
|  | iii) | Third party liability insurance | Lump sum |  |  |  |
|  | iv) | Professional liability insurance | Lump sum |  |  |  |
| 5 | Drafting, reproduction of reports |  | Lump sum |  |  |  |
| 6 | Office rent |  | Per month |  |  |  |
| 7 | Others4 |  | TBD |  |  |  |
| TOTAL FINANCIAL OFFER (Fees + Reimbursable expenses) |  |  |  |  |  |  |

3. The payment shall be made in accordance with the agreed schedule in line with the deliverables

4. Payment Conditions: Payment shall be made in US Dollars not later than 30 days following submission of original invoice by the Individual Consultant, in duplicate, accompanied by the requested supporting documents. All payments under the contract shall be made by bank transfer into the bank account indicated by the Individual Consultant in her/his invoices.

Amounts must coincide with the ones indicated under Total Cost of Financial proposal in Form FIN-2.

The proof of stated qualifications shall be in the form of the copies of the degrees and diploma obtained, while for the professional experience the proof shall be either acknowledgement letters from the previous employers or copies of the Purchase Order/ Contract signed with them.

Delete items that are not applicable or add other items as the case may be.

Indicate unit cost..

Indicate route of each flight, and if the trip is one- or two-ways

Provide clear description of what is their exact nature

Delete items that are not applicable or add other items as the case may be.

Indicate route of each flight, and if the trip is one- or two-ways.

Indicate unit cost.

Provide clear description of what is their exact nature