## Slide 1: HIV/AIDS GRANTS INFORMATION SESSION
Directorate of Policy, Planning and Resource Mobilisation (PPRM)
22 May 2025

## Slide 2: OUTLINE
Monitoring and Evaluation of Grants
Logical Framework
M&E Plans
Key Performance Indicators Monitored
Reporting Requirements
Governance Structures
Cross Cutting Issues
Stakeholders Analysis

## Slide 3: 1. Monitoring and Evaluation of Grants
Grants are to demonstrate how they will carry monitoring and evaluation activities (Baseline, Monitoring and Evaluation processes and products).
Use Logical Framework as an approach to monitoring.
Plans for putting in place project monitoring tools based on the logical framework.
Outline Data collection procedures

## Slide 4: 2. Logical Framework
Fully developed Logical Frameworks
Outline the intervention logic (vertical and horizontal)
SMART – Specific, Measurable, Attainable, Realistic, Time Bound indicators.
Baselines and Targets

## Slide 5: 3. M&E Plans
Developed for every project
Outlines indicators and definition of indicators
Data collection methods
Data sources
Frequency of data collection
Responsibility
Linked to ITT (tracks performance against indicators)

## Slide 6: 4. Key Performance indicators Monitored
Accountability
Compliance
Budget utilization
Implementation of activities (including procurement of goods, services and works)
Achievement of results – Results Framework
Risk factors

## Slide 7: 5. Reporting Requirements
Report for results linked to the Logical Framework (and linked to resources)- Effectiveness, Efficiency and Value for money
Quarterly and Annual Grant Management Reports
Include lessons (positive and negative lessons), Change stories, issues and mitigation measures
Reports review processes – MOH and NAC
Field Visits – Expenditure Verifications

## Slide 8: 6. Governance Structures
Internal
External
Project Technical Meetings – Meeting of project Experts duly constituted for the purpose
Coordination – in country and between participating MS

## Slide 9: 7. Cross Cutting Themes
Gender
Participation
Conflict prevention
Vulnerability and Disability
Environment /Climate Change

## Slide 10: 8. Stakeholders Analysis
Stakeholders Engagement Plan
Stakeholders’ Meetings
Roles and Responsibilities
Communication mechanisms
Collaboration