## Goods
Detailed Procurement Plan - Procurement of Goods & Works
Country / Executing Agency |  |  | SADC
Name of Project/Program |  |  | RHeSEP Project
Loan No.
Basic Data | [11 empty] | Bidding Document |  | Bidding Period |  | Bid Evaluation *++ |  | Contract Finalization
Procurement System* | Package No. | Package Descritption | Lot No.+ | Lot Description+ | Issue No. Invitation for Bids | Lump Sum or Bill of Quantities | Estimated Cost UA | Procurement Method | Pre-or-Post Qualification | Oversight Audit Prior-or-Post Review*** | Plan Revised Actual*+ | Date Submitted | Date No Objection | Date Bid Invitation (SPN) | Date Bid Closing/ Opening | Date Bid Evaluation Report Submitted | Date No-Objection | Date Contract Award | Contract Amount (Currency)*+++ | Date Contract Signature | Date Contract Completion
Third Party |  | Procure assorted laboratory equipment for WES and diagnostic laboratories for 6 countries | 6 |  |  |  | 1,006,805 | WHO |  |  | Plan |  |  | 15-04-2027
Revised
Actual
Third Party |  | Procure and instal mobile cross-border laboratories at the border points in Mozambique and Zimbabwe | 1 |  |  |  | 272.774 | WHO |  |  | Plan |  |  | 15-06-2026
Revised
Actual
BPMP |  | Procure office equipment | 1 | N/A | N/A | BoQ | 6244 | RFQ | N/A | Post | Plan | N/A | N/A | 2026-03-01 | 2026-03-15 | N/A | N/A | 2026-04-14 |  | 2026-04-19 | 2026-05-19
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Total Cost | [6 empty] | 1007077.774 |  |  |  | Plan
Revised
Actual
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
+ | If applicable
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
*++ | The template is to be adapted in case of two stage bidding by adding columns for the second stage bidding period and evaluation process
*+++ | Indicate currency of the contract
Formulas:
Date Bid Closing/ Opening = [Bidding Period]+14
Contract Finalization = [Date Bid Closing/ Opening]+30
Date Contract Signature = [Contract Finalization]+5
Date Contract Completion = [Date Contract Signature]+30

## Works
Detailed Procurement Plan - Procurement of Goods & Works
Country / Executing Agency |  |  | Multinational/ SADC
Name of Project/Program |  |  | RESILIENT HEALTH SYSTEMS FOR EMERGENCY PREPAREDNESS PROJECT
Loan No.
Basic Data | [11 empty] | Bidding Document |  | Bidding Period |  | Bid Evaluation *++ |  | Contract Finalization
Procurement System* | Package No. | Package Descritption | Lot No.+ | Lot Description+ | Issue No. Invitation for Bids | Lump Sum or Bill of Quantities | Estimated Cost UA** | Procurement Method | Pre-or-Post Qualification | Oversight Audit Prior-or-Post Review*** | Plan Revised Actual*+ | Date Submitted | Date No Objection | Date Bid Invitation (SPN) | Date Bid Closing/ Opening | Date Bid Evaluation Report Submitted | Date No-Objection | Date Contract Award | Contract Amount (Currency)*+++ | Date Contract Signature | Date Contract Completion
Third Party | 1 | Civil works for renovation of WES and diagnostic laboratories in 6 countries | 6 |  |  | BoQ | 580975 | WHO | Post | Audit | Plan | N/A | N/A | 2026-06-16 | 2026-07-28 | 2026-08-18 | N/A | 2026-09-29 |  | 2026-10-06 | 2027-04-04
[11 empty] | Revised | [9 empty] | .
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Plan
Revised
Actual
Total Cost | [10 empty] | Plan
Revised
Actual
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
+ | If applicable
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
*++ | The template is to be adapted in case of two stage bidding by adding columns for the second stage bidding period and evaluation process
*+++ | Indicate currency of the contract
Formulas:
Date Bid Closing/ Opening = [Bidding Period]+42
Bid Evaluation *++ = [Date Bid Closing/ Opening]+21
Contract Finalization = [Bid Evaluation *++]+42
Date Contract Signature = [Contract Finalization]+7
Date Contract Completion = [Date Contract Signature]+180

## Consulting Services
Detailed Procurement Plan - Procurement of Consulting Services
Country / Executing Agency |  | Multinational/ SADC
Name of Project/Program |  | RESILIENT HEALTH SYSTEMS FOR EMERGENCY PREPAREDNESS PROJECT
Loan No.
Basic Data | [6 empty] | REOI |  | Terms of Reference |  | Short List |  |  | Request for Proposals (RFP) |  |  |  | Evaluation of Proposals | [5 empty] | Contract Finalization
Procurement System* | Description | Selection Method | Lumpsum or Time-Based | Estimated Cost UA | Oversight Audit Prior- or-Post Review*** | Plan Revised Actual*+ | Date Published | Date Closing | Date Submitted | Date No-Objection | Date Submitted | Date Approved | Plan Revised Actual | Date RFP Documents Submitted | Date No-Objection | Date RFPs Issued | Date Proposals Closing - Opening | Date Technical Report Submitted | Date No-Objection | Date Opening Financial Proposals | Date Combined Report Submitted | Date No-Objection | Plan Revised Actual | Date Contract Award | Contract Amount Currency*++ | Date Contract Signature | Date Contract Completion
BPMP | Development and finalisation of the SADC Regional Strategy on One Health | ICS | Lumpsum | 46828 | Post | Plan | 2026-06-01 | 2026-06-15 | 2026-05-15 | 2026-05-29 | 2026-07-06 | 2026-07-20 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-08-10 |  | 2026-08-24 | 2026-12-10
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Establish a model for cross-border laboratories in SADC | CQS | Lumpsum | 117070.305 | Prior | Plan | 2026-06-01 | 2026-06-15 | 2026-05-15 | 2026-05-29 | 2026-07-06 | 2026-07-20 | Plan | 2026-07-06 | 2026-07-20 | 2026-07-23 | 2026-09-03 | 2026-09-24 | 2026-10-08 | 2026-10-22 | 2026-11-05 | 2026-11-12 | Plan | 2026-11-26 |  | 2026-12-10 | 2027-06-10
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Third Party | TA on regulatory systems, sciences and enabling environment for local production | WHO | Time-based | 351211 | Audit | Plan | 2026-04-01 | 2026-04-15 | 2026-05-15 | 2026-05-29 | 2026-05-06 | 2026-05-20 | Plan | 2026-05-06 | 2026-05-20 | 2026-05-23 | 2026-07-04 | 2026-07-25 | 2026-08-08 | 2026-08-22 | 2026-09-05 | 2026-09-12 | Plan | 2026-09-26 |  | 2026-10-10 | 2028-10-10
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Consultant to support MRH Institutionalisation | ICS | Lumpsum | 280969 | Prior | Plan | 2026-07-15 | 2026-07-29 | 2026-05-15 | 2026-05-29 | 2026-08-19 | 2026-09-02 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-09-23 |  | 2026-10-07 | 2028-10-07
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Support establishment of an Infirmation Management System - Madagascar | ICS | Lumpsum | 46828 | Post | Plan | 2026-07-15 | 2026-07-29 | 2026-05-15 | 2026-05-29 | 2026-08-19 | 2026-09-02 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-09-23 |  | 2026-10-07 | 2027-04-07
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Technical Assistance for pooled procurement | ICS | Time-based | 234141 | Prior | Plan | 2026-07-15 | 2026-07-29 | 2026-05-15 | 2026-05-29 | 2026-08-19 | 2026-09-02 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-09-23 |  | 2026-10-07 | 2028-10-10
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
Actual
BPMP | TA on the establishment of Long-Term Agreements (LTA) with Suppliers | ICS | Lumpsum | 105363 | Prior | Plan | 2027-01-01 | 2027-01-15 | 2026-05-15 | 2026-05-29 | 2027-02-05 | 2027-02-19 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2027-03-12 |  | 2027-03-26 | 2029-04-01
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Third Party | Build capacities on pooled procurement best practices, draft reports, and orgaize validation workshops | WHO | Lumpsum | 117070 | Audit | Plan | 2027-01-01 | 2027-01-15 | 2026-05-15 | 2026-05-29 | 2027-02-05 | 2027-02-19 | Plan | 2027-02-05 | 2027-02-19 | 2027-02-22 | 2027-04-05 | 2027-04-26 | 2027-05-10 | 2027-05-24 | 2027-06-07 | 2027-06-14 | Plan | 2027-06-28 |  | 2027-07-12 | 01 Ju;y 2029
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual
BPMP | Technical assistance for the Innovation Challenge/Consulancy Firm | CQS | Lumpsum | 78047 | Post | Plan | 2026-06-01 | 2026-06-15 | 2026-05-15 | 2026-05-29 | 2026-07-06 | 2026-07-20 | Plan | 2026-07-06 | 2026-07-20 | 2026-07-23 | 2026-09-03 | 2026-09-24 | 2026-10-08 | 2026-10-22 | 2026-11-05 | 2026-11-12 | Plan | 2026-11-26 |  | 2026-12-10 | 2027-06-01
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Consultancy services to expand the SADC CBRS into the RHIMS | QCBS | Lumpsum | 234141 | Prior | Plan | 2026-06-15 | 2026-06-29 | 2026-05-15 | 2026-05-29 | 2026-07-20 | 2026-08-03 | Plan | 2026-07-20 | 2026-08-03 | 2026-08-06 | 2026-09-17 | 2026-10-08 | 2026-10-22 | 2026-11-05 | 2026-11-19 | 2026-11-26 | Plan | 2026-12-10 |  | 2026-12-24 | 01 Junary 2029
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Technical support on the CBRS/M&E/consultancy | ICS | Time-based | 280969 | Prior | Plan | 2025-11-17 | 2025-12-01 | 2026-05-15 | 2026-05-29 | 2025-12-22 | 2026-01-05 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-01-26 |  | 2026-02-09 | 2028-02-01
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Third Party | Undertake a health systems functionality and performance assessment for the SADC region | WHO | Lumpsum | 163898.427 | Audit | Plan | 15-06-2026 | 2026-06-29 | 2026-05-15 | 2026-05-29 | 2026-07-20 | 2026-08-03 | Plan | 2026-07-20 | 2026-08-03 | 2026-08-06 | 2026-09-17 | 2026-10-08 | 2026-10-22 | 2026-11-05 | 2026-11-19 | 2026-11-26 | Plan | 2026-12-10 |  | 2026-12-24 | 2027-12-01
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
Third Party | Conduct a baseline analysis of the health system's adaptation and resilience to shocks, including climatic and environmental shocks in three countries (Malawi, Mozambique, Lesotho) | QCBS | Lumpsum | 234140.61 | Audit | Plan | 2026-06-15 | 2026-06-29 | 2026-05-15 | 2026-05-29 | 2026-07-20 | 2026-08-03 | Plan | 2026-07-20 | 2026-08-03 | 2026-08-06 | 2026-09-17 | 2026-10-08 | 2026-10-22 | 2026-11-05 | 2026-11-19 | 2026-11-26 | Plan | 2026-12-10 |  | 2026-12-24 | 2028-12-01
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Consultancy services for the feasibility study for inclusion of public health into the SADC Shock | ICS | Lumpsum | 78047 | Post | Plan | 2026-09-15 | 2026-09-29 | 2026-05-15 | 2026-05-29 | 2026-10-20 | 2026-11-03 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-11-24 |  | 2026-12-08 | 2027-06-01
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Project Coordinator, | ICS | Time-based | 280968.731 | Prior | Plan | 2026-01-12 | 2026-01-26 | 2025-12-15 | 2025-12-29 | 2026-02-16 | 2026-03-02 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-03-23 |  | 2026-04-06 | 2030-04-05
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Procurement Expert, | ICS | Time-based | 233204 | Prior | Plan | 2026-01-12 | 2026-01-26 | 2025-12-15 | 2025-12-29 | 2026-02-16 | 2026-03-02 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-03-23 |  | 2026-04-06 | 2030-04-05
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Finance Officer | ICS | Time-based | 117070 | Prior | Plan | 2026-01-12 | 2026-01-26 | 2025-12-15 | 2025-12-29 | 2026-02-16 | 2026-03-02 | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 2026-03-23 |  | 2026-04-06 | 2030-04-05
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
BPMP | Audit services | LCS | Lumpsum | 14048 | Prior | Plan | 2026-11-17 | 2026-12-01 | 2026-05-15 | 2026-05-29 | 2026-12-22 | 2027-01-05 | Plan | 2026-12-22 | 2027-01-05 | 2027-01-08 | 2027-02-19 | 2027-03-12 | 2027-03-26 | 2027-04-09 | 2027-04-23 | 2027-04-30 | Plan | 2027-05-14 |  | 2027-05-28 | 2028-05-27
|  |  |  | 0 |  | Revised | [6 empty] | Revised | [9 empty] | Revised
|  |  |  | 0 |  | Actual | [6 empty] | Actual | [9 empty] | Actual
Total Cost |  |  |  | 2999966.073 |  | Plan | [6 empty] | Plan | [9 empty] | Plan
[6 empty] | Revised | [6 empty] | Revised | [9 empty] | Revised
[6 empty] | Actual | [6 empty] | Actual | [9 empty] | Actual
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Retain procurement "Plan" agreed at negotiations and approved by the Boards throughout the project duration
"Revised" includes all updates and revisions
Record the "Actual" date of completion of the activity
*++ | Indicate currency of the contract
Formulas:
Date Closing = [REOI]+14
Date No-Objection = [Terms of Reference]+14
Date No-Objection = [Request for Proposals (RFP)]+14
Short List = [Date Closing]+21
Date Approved = [Short List]+14
Contract Finalization = [Date Approved]+21
Contract Finalization = [Date No-Objection]+14
Date Contract Signature = [Contract Finalization]+14
Request for Proposals (RFP) = [Short List]
Date RFPs Issued = [Date No-Objection]+3
Date Proposals Closing - Opening = [Date RFPs Issued]+42
Evaluation of Proposals = [Date Proposals Closing - Opening]+21
Date Opening Financial Proposals = [Date No-Objection]+14
Date Combined Report Submitted = [Date Opening Financial Proposals]+14
REOI = [Date No-Objection]+14
Date Contract Completion = [Date Contract Signature]+1460
Note on AB8: MANDO, HAZEL KASHOKI: INSERT COMPLETION DATE BASED ON ESTIMATED PERIOD FOR CONDUCTING ACTIVITY IN DAYS (Contract Signature+Days for completion)

## Simplified Procurement Plan
Simplified Procurement Plan - Procurement of Goods, Works & Consultng Services
Country / Executing Agency |  | Southern African Development Community (SADC)
Name of Project/Program |  | Resilient Health Systems for Emergency Preparedness (RHeSEP) Project
Loan No.
Procurement Template Simplified Version
Procurement System* | Package No. | Package Descritption | Category~ | Estimated Cost UA | Procurement Method | Oversight Audit Prior-or-Post Review*** | Date SPN Published | Date Bid/Proposals Closing/ Opening | Date Contract Award | Contract Amount (UA)*+ | Date Contract Completion | Comments for Contract Execution
Third Party | 1 | Procure assorted laboratory equipment for WES and diagnostic laboratories for 6 countries | Goods | 1,006,805 | WHO | Audit | 15-04-2027 |  | 10-08-2026 | 1,006,805
Third Party | 2 | Procure and instal mobile cross-border laboratories at the border points in Mozambique and Zimbabwe | Goods | 272.774 | WHO | Audit | 15-06-2026 |  |  | 272.774
BPMP | 3 | Procure office printer | Goods | 6244 | RFQ | Post | 2026-03-01 | 2026-03-15 | 2026-04-14 | 6244 | 2026-12-10
Third Party | 4 | Civil works for renovation of WES and diagnostic laboratories in 6 countries | Works | 580975 | WHO | Audit | 01-06-2026 | 14-07-2026 | 08-09-2026 | 580975 | 2027-04-04
BPMP | 5 | Development and finalisation of the SADC Regional Strategy on One Health | Services | 46828 | ICS | Post | 01-06-2026 | 03-09-2026 | 26-09-2026 | 46828 | 2027-06-10
BPMP | 6 | Establish a model for cross-border laboratories in SADC | Services | 117070 | CQS | Prior | 01-06-2026 | 04-07-2026 | 23-09-2026 | 117070 | 2028-10-07
Third Party | 7 | TA on regulatory systems, sciences and enabling environment for local production | Services | 351211 | WHO | Audit | 01-04-2026 | N/A | 23-09-2026 | 351211 | 0
BPMP | 8 | Consultant to support MRH Institutionalisation | Services | 280969 | ICS | Prior | 15-07-2026 | N/A | 23-09-2026 | 280969 | 2027-04-07
BPMP | 9 | Support establishment of an Infirmation Management System - Madagascar | Services | 46828 | ICS | Post | 15-07-2026 | N/A | 12-03-2027 | 46828 | 2028-10-10
BPMP | 10 | Technical Assistance for pooled procurement | Services | 234141 | ICS | Prior | 15-07-2026 | N/A | 10-12-2026 | 234141 | 2029-04-01
BPMP | 11 | TA on the establishment of Long-Term Agreements (LTA) with Suppliers | Services | 105363 | ICS | Prior | 01-01-2027 | N/A | 26-01-2026 | 105363 | 2027-06-01
Third Party | 12 | Build capacities on pooled procurement best practices, draft reports, and orgaize validation workshops | Services | 117070 | WHO | Audit | 01-01-2027 | 05-04-2027 | 28-06-2027 | 117070 | 2028-10-07
BPMP | 13 | Technical assistance for the Innovation Challenge/Consulancy Firm | Services | 78047 | CQS | Post | 01-06-2026 | 03-09-2026 | 26-11-2026 | 78047 | 01 Junary 2029
BPMP | 14 | Consultancy services to expand the SADC CBRS into the RHIMS | Services | 234141 | QCBS | Prior | 15-06-2026 | 17-09-2026 | 10-12-2026 | 234141 | 2028-02-01
BPMP | 15 | Technical support on the CBRS/M&E/consultancy | Services | 280969 | ICS | Prior | 17-11-2025 | N/A | 26-01-2026 | 280969 | 2027-06-01
Third Party | 16 | Undertake a health systems functionality and performance assessment for the SADC region | Services | 163898 | WHO | Audit | 15-06-2026 | N/A | 10-12-2026 | 163898 | 0
Third Party | 17 | Conduct a baseline analysis of the health system's adaptation and resilience to shocks, including climatic and environmental shocks in three countries (Malawi, Mozambique, Lesotho) | Services | 234141 | WHO | Audit | 15-06-2026 | 17/09/2026 | 10-12-2026 | 234141 | 0
BPMP | 18 | Consultancy services for the feasibility study for inclusion of public health into the SADC Shock | Services | 78047 | QCBS | Post | 15-09-2026 | N/A | 24-11-2026 | 78047 | 2028-10-10
BPMP | 19 | Project Coordinator, | Services | 280969 | ICS | Prior | 2026-01-12 | N/A | 2026-03-23 | 280969 | 2027-06-01
BPMP | 20 | Procurement Expert | Services | 233204 | ICS | Prior | 2026-01-12 | N/A | 2026-03-23 | 233204 | 2030-04-05
BPMP | 21 | Assistant Finance Officer | Services | 117070 | ICS | Prior | 2026-01-12 | N/A | 2026-03-23 | 117070 | 2030-04-05
BPMP | 22 | Audit services | Services | 14048 | LCS | Prior | 17-11-2026 | 19-02-2027 | 14-05-2027 | 14048 | 2028-05-27
Total Cost |  |  |  | 3601233
* | Insert Procurement System or Regime for the procurement transatction under the project (i.e. BPS, Bank or Third Party)
~ | Indicate Goods, Works, non-consulting or Consulting Services
** | Total cost of the package or lot or procurement transaction in UA from the PAR
*** | Indicate oversight modality (i.e. procurement audit if BPS or post or prior review for Bank methods or reports for third party)
*+ | Indicate currency of the contract
Formulas:
Date Bid/Proposals Closing/ Opening = [Date SPN Published]+14
Date Contract Award = [Date Bid/Proposals Closing/ Opening]+30